## Sheet1
Partners' Action Plan - MINARET Project
No. | Activity | Decription | Deliverable | 2019 | [11 empty] | Responsibility | Notes | Started (Yes/No)
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | 1.2.3 Prepare a Case Study on one municipality with Best Municipality Practices to Encourage NEXUS Thinking & Application. | look up different Nexus project(s)/plan(s), by municipalities that are active members of the Covenant of Mayors. Further, explain the strategy the project(s)/plan(s) uses and its goals, achievements and limitations | Case Study Report | [12 empty] | Muhieedin Tawalbeh |  | Yes
2 | 2.3 Develop and implement detailed capacity building and training & awareness plan & material relevant to planning, implementation, maintenance & monitoring of water & energy Pilot Projects and Socio-Economic Projects with the aim of introducing Job opportunities for local community specifically women & youth. | Where training gaps exist, design training plan to meet the needs training audiences and prepare training material make them available in a variety of formats such as training manuals, PowerPoint, pdf files. This material will be uploaded in the online platform to be consulted when needed. the training will include topics on energy efficiency & renewable energy and their relevancy to Nexus approach, Covenant of Mayors (reporting and monitoring of action plan (SECAP)), access to finance | Training and Awareness Plan with the Required Material | [12 empty] | Muhieedin Tawalbeh |  | No
3 | 4.1 Implement pilot projects for renewable energy & energy efficiency in the three selected Municipalities. | Lebanon: 1- PV installation and lighting replacement projects - Prepare technical specifications. - Tender document preparing. - Tender announcement. - Offers’ evaluation and awarding. - Project execution and supervision & commissioning. Tunisia: 1- street lighting replacement project. - Prepare technical specifications. - Tender document preparing. - Tender announcement. - Offers’ evaluation and awarding. - Project execution and supervision. 2- Purchasing an electric car (EV) for the Municipality. - Selection of EV from Joradn Market - EV shipping - Tendering process for the PV charging station - Installation of charging station - implemntation and Jordan: 1- Implementing a nursery Plant: - Prepare technical specifications. - Tenders/procurement documents preparation - Tender/procurement announcements. - Offers’ evaluation and awarding. - Project execution and supervision. | Pilote RE&EE Projects Report for each Municipality | [12 empty] | Muhieedin Tawalbeh |  | Yes
4 | 4.2 Support small initiatives for Community Based Organizations & NGOs, with particular attention to women, that enable them to better use/optimize natural resources to generate economic, social and environmental benefits and in the process, enhance women's role in sustainable development. Implement the value chain socio-economic projects within municipalities in partnership with Community Based Organizations & NGOs. | Lebanon: - Prepare technical specifications for PV installation for the Local CBO for Green Farm projects. - Tender document preparing. - Tender announcement. - Offers’ evaluation and awarding. - Project execution and supervision. | [13 empty] | Muhieedin Tawalbeh |  | Yes
5 | 5.1 Develop Sustainable Energy Action Plans (SECAP) for Monastir & Al-Jdaideh Municipalities and propose any potential update to the developed SECAP for Karak Municipality, and Perform follow up on Covenant of Mayors requirements | Lebanon: -Prepare an approved final Baseline Emission Inventory report. -Prepare the required official document to be a member in the covenant of Mayors. -Prepare final draft of the Sustainable Energy and Climate Action Plan (SECAP). Tunisia: -Prepare an approved final Baseline Emission Inventory report. -Prepare the required official document to be a member in the covenant of Mayors. -Prepare final draft of the Sustainable Energy and Climate Action Plan (SECAP). Jordan: -Update and review the Sustainable Energy and Climate Action Plan (SECAP), where needed. | Final SECAP Reports for the three Municipalities | [12 empty] | Muhieedin Tawalbeh |  | Yes