## AM Plan
Horizons Action Plan - MINARET Project
No. | Activity | Decription | Deliverable | 2019 | [12 empty] | 2020 |  |  | Responsibility | Notes | Started (Yes/No)
|  |  |  | Jul | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
2.2 | VCM and Capacity Building | Finalize VCM and CB by receiving finalized reports from ACS and Qperspective complete with any comments provided by Horizons, and complete all payments | ACS: Modified Final Report, Qperspective: Modified 3rd and final report. | [16 empty] | Horizons | VCM Completed in September but financial documents are yet to be submitted, hence the delay | Yes | bar: 2019 Feb to 2019 Aug
1.4 | Gender mainstreaming | Develop the gender mainstreaming action plan | Gender Mainstreaming Action Plan Report | [16 empty] | Horizons | Gender baseline available | Yes | bar: 2019 Nov
4.1/4.2 | Water pilot action and socioeconomic | Finalize all tendering and procurement for water pilot actions and socioeconomic activities | Signed contracts with suppliers and contractors, all pilot action and SE activities begin in 3 countries | [16 empty] | Horizons |  | Yes | bar: 2019 Jun to 2019 Aug
4.2 | Socioeconomic | Complete all SE activities | Completed SE activities | [16 empty] | Horizons | Lebanon and Jordan SE done in Nov, delays in Lebanon caused by protests | Yes | bar: 2019 Mar to 2019 Aug; 2019 Nov to 2019 Dec
2.3 | Capacity Building | Finalize capacity building plan and begin training | Capacity building plan document, conducted trainings, trained stakeholders in 3 municipalities. | [16 empty] | Horizons & NERC | Plan to be finished in August and training to take place sep-mar 2020 | Yes | bar: 2019 Aug; 2019 Nov to 2020 Mar
4.1 | Tunisia water pilot action | Complete water pilot action in Tunisia | Installed and functional water harvesting system in Monastir | [16 empty] | Horizons | Work has begun on the ground as of October | Yes | bar: 2019 Nov to 2019 Dec
4.1 | Lebanon water pilot action | Complete water pilot action in Lebanon | Installed and functional irrigation system in Jdeideh | [16 empty] | Horizons & NERC |  | Yes | bar: 2019 Mar to 2019 Aug
5.4 | Access to Finance | Sign with Greentech and complete AtF activity in 3 municipalities | Comprehensive report on 3 municipalities, at least one secured investment, and established investment funds in municipalities | [16 empty] | Horizons & PMU | Finalize contract in Sep and begin work after | Yes | bar: 2019 Nov to 2019 Dec