## MINARET TaskList
Tasks List - 2019
Start Date | TASK | Description | Action Person/s | NOTES | DONE
Com. Ofr. Recruitement
22/7/19 | TOR developed and finalized | PM developed TOR and obtained consensus from Ips | Rula / IPs |  | 1
25/7/19 | To announce vacancy | To post vancancy on job search engine and coordinate with RSS/HR | Dana |  | 0
0
0
| Website / Platfprm Development |  |  |  | 0
24/7/19 | Meeting with IT | Requirements on web/platform were set with IT co. | Rula / IT / IUCN |  | 1
| Website content | IT will work on requirements and to receive from nerc content details, clear points disscussed | Dana / Monther |  | 0
0
0
| IPS' Action Plan |  |  |  | 0
24/7/19 | Email sent to IPS | IPS to present their action plans by 4th of Aug till end of 2019 | Dana |  | 0
0
| Monthly Progress Report |  |  |  | 0
16/7/19 | Email sent to IPS | NERC + IPS to submit their monthly progress reports for the first half of 2019, and to adop this as a norm throughout the project lifetime | Dana |  | 0
0
| Financial Control |  |  |  | 0
| email sent to IPS on this regards | IPS to prepare for visit and close up financial claims | Ahmad |  | 0
| 2019 Forecast |  | Ahmad |  | 0
| Newsletter |  |  |  | 0
21/7/19 | Setting requirements | Bold guidelines given to Monther to lead on that | Monther / Dana |  | 0
0
0
| M&E |  |  |  | 0
| ME&E Training | Feedback is awaited on the results obtained from the training | Dana / Ali |  | 0
0
| Annual Meeting [Beirut] |  |  |  | 0
22/7/19 | Coordination with ESCWA to host | Meeting held with Radia to set the basic ground for the meeting and agreeing on the tentative dates | Muhie / Rami/ Rula |  | 0
23/7/19 | Pre-travel preparations | Participants selection criteria submitted | Rami |  | 0
0
0
0
| Annual Review Meeting [SIDA] |  |  |  | 0
24/7/19 | Compliance to requirements | Fianalized Annual Progress Report for 2018 + Budget/workplan/workplan differences for 2019 + TOC (with rational of change) submitted to SIDA | Rula / Muhie / Ahmad / Dana |  | 0
| Reviewing Achievement | Annual review meeting to take place on 24/7 | SIDA + MINARET IPS |  | 0
0
0
| Printed Items |  |  |  | 0
0
1
| Capacity Building |  |  |  | 0
3
4
5
6